Action Plan Pertaining to Sale of Banks Placed

# Under Control of Savings Deposits Insurance Fund

1. Preparation of banks, management and shares of which have been transferred to the Savings Deposits Insurance Fund, for sale;

1.1. Completion of a review of financial conditions of the banks managed by the Fund, preparation of their financial statements as of August 2000 when the Savings Deposits Insurance Fund was transferred to the Banking Regulation and Supervision Agency (this process has been completed.)

1.2 Assessment of quality of the banks' assets (this process has been completed.)

1.3) Determination by the Banking Regulation and Supervision Board of types of assets to be taken over by the Asset Management Unit created within the Savings Deposits Insurance Fund and conditions for such transfer,

1.4) Elimination of the banks' bad assets (exclusion of losses and bad debts from their balance sheets) and determination of funds necessary for capital adequacy ratio for each bank and for all the banks (this process has been completed).

1.5) Implementation of the common management procedure adopted for addressing such issues as rehabilitation of banks, an efficient use of resources, pursuing their rights, receivables and litigations and ensuring their efficient management and implementation of the action plan by all banks in an harmonious manner, and application of decisions made by boards of directors of the Banking Regulation and Supervision Board and the Savings Deposits Insurance Fund (this process has been completed).

2.  Determination of requirements to be met by applicants who intend to purchase shares of banks managed by the Savings Deposits Insurance Fund (this process has been completed).

3. Purchasing of Special Category State Public Borrowing Notes, which are needed to improve financial conditions of banks and to be borrowed from the Treasury Undersecretariat by determining conditions regarding their repayment, term, type and interest rates (this process has been completed)

4. Completion of investigations related to investors and review by investors of the banks.

4.1. Issuing invitations to potential buyers who will apply to the Savings Deposits Insurance Fund in order to purchase shares of the banks and submission of their application forms to the Agency (to be completed on December 15)

4.2 Approval by the Board of buyers who meet requirements laid down by the Board and informing them of the result (to be completed on December 22).

4.3 Signing confidentiality agreements with investors who meet specified requirements and permitting them to carry out reviews and inspections in banks in which they are interested (to be completed in January 2001).

4.4 Receipt and evaluation of proposals submitted by organizations which have performed required reviews (to be completed in February 2001)

5. Preparation by the Savings Deposits Insurance Fund of tender specifications, release of tender notices (to be completed in February 2001).

6. Preparation by investors of their proposals by taking conditions set forth in the specifications and obtaining all kinds of information relevant to the banks and by also causing performance of a "due diligence" study where deemed necessary and submission of these proposals to the Fund (to be completed in the first week of April 2001).

7. Evaluation of proposals and completion of bidding processes (to be completed by the end of April 2001).

8. Signing of sale agreements and transfer of shares.